## Sheet1
R. D. Construction
Civil Engineers & Contractors
28, Apratim Pushp, Behind Radha Mangal Karyalaya, Satara Parsar, Aurangabad – 431001
HAZARD IDENTIFICATION AND RISK ASSESSMENT ( HIRA ) -DEVELOPMENT OF RISK CONTROL MEASURES
ACTIVITY - 1: MANUAL EXCAVATION
1 | Pit Excavation upto 3m | 1. Falling into pit. 2. earth collapse. 3. Contact with buried electric 4. Gas/Oil Pipelines. | 1. Personal injury. 2. Suffocation/Breathlessnes. 3. Buried. 4. Electrocution. 5. Explosion. | 3 | 4 | MODERATE | 3 | 1. Provide guardrails/barricade with warning signal. 2. Provide atleat two entries/exits. 3. Provide escape ladder. 4. Provide suitable size of shoring and strutting if required. 5. Keep soil heeps away from edge equivalent to 1.5m or depth of pit whichever is more. 6. Do not allow vehicles to operate too close to excavated areas. Maintain atleast 2m distance from edge of cut.
7. Maintain sufficient angle of repose. Provide slope not less than 1:1 and suitable bench of 0.5m width at every 1.5m depth of excvation in all soil except hard rock. 8. Battering/Benching the sides. 9. Obtain permission from component authorities prior to excavation, if required. 10. Locate the position of buried utility by refering to plant 11. Start digging manually to locate the exact position of buried utility and therafter use mechanical means.
ACTIVITY - 2: REINFORCEMENT
1 | Reinforcement | 1. Curtailment and binding of 2. Carrying of rods for short distance/at height. 3. Checking of clear distance/cover with hands. 4. Hitting projected rods and standing on cantiliver rods. | 1. Persons may get injured. 2. Workers may get injured on their hands and soulders. 3. Rods may cut or injure the fingers. 4. Persons may get injured and fall down. 5. May prove fatal. 6. Protruded rods may hit the persons. | 3 | 3 | MODERATE | 3 | 1. Use PPE like gloves, shoes, helmets, etc.. 2. Avoid usage of make -shift tools. 3. Provide suitable pads on shoulders and use safety gloves. 4. Tie up rods in easily liftable bundles. 5. ensure proper staging. 6. Use measuring devices like tape, measuring rods,etc.. 7. Use safety shoes and avoid standing unnecessarily on cantilever rods. 8. avoid wearing of loose cloths. 9. Provide safety nets.
2 | Transportation of Rebar | 1. Fall of material from height. 2.Hit by protruding bar. | 1. Personal injury. 2. May prove fatal. 3. damage to Material/Property | 4 | 3 | MODERATE | 3 | 1. Use red flags/lights at the end. 2. Do not protrude the rods infront of or by the side of the dricers cabine. 3. Do not extend the rods 1/3rd of deck length or 1.5m whichever is less.
ACTIVITY - 3: SHUTTERING AND SHORING
1 | Shutterinh/Handel ing of wooden planks and | 1. Protruding nails. 2. Unsafe/Improper handling. 3. Improper housekeeping. | 1. Personal injury. 2. Tripping/slipping hazard. | 3 | 4 | MODERATE | 3 | 1. Avoid Protrusion/projection of sharp edges. 2. Secure the load properly. 3. See that there is no strain on back.
2 | Cutting wood to required size. | 1. Misuse of cutting device. 2. Fall of tools and wood from height. | 1. Hand injury. 2. Improper cutting resulting in material loss. 3. Personnel injury. | 3 | 3 | LOW | 2 | 1. Deploy trained carpenter.
3 | Preparation of shuttering on ground. | 1. Flying nails while hammering. 2. Use of loose hammer. | 1. Eye injury. 2. Flying of hamme head resulting in personnel injury. | 3 | 4 | MODERATE | 3 | 1. Wear safety goggles. 2. Ensure that hammer handle is properly wedged and hammer is in good condition. 3. Keep persons away from hammering area.
4 | Erection of shuttering. | 1. Fall of shuttering. | 1. Physical injury and back pain. | 2 | 4 | MODERATE | 3 | 1. Erection should be done standing over firm supports.
5 | Erection of shuttering on height. | 1. Fall of person or sutter. 2. Fall of loose materials. | 1. Personal injury. 2. Damage to the shutter. 3. Loss of materils. | 3 | 4 | MODERATE | 3 | 1. Use approved scaffolding. 2. Do not keep loose material on platform. 3. Deploy experienced workers.
6 | De-shuttering & De-shoring | 1. Fall of shuttering. 2. Protruding nails. 3. Loose nails on floor. | 1. Injury to persons. | 2 | 3 | LOW | 2 | 1. Deploy experienced workers. 2. Keep and alert third party persons to be away from the de- shuttering area. 3. Remove nails and stack shuttering materials properly. 4. Keep all removed nails in one container. 5. Maintain good housekeeping.
ACTIVITY - 4: CONCRETING
1 | Concreting | 1. Air pollution by cement. 2. Handling of Ingredients. 3. Protruding reinforced rods. 4. Earthing of electrical mixers, vibrartors etc.. Not done. 5. Falling of materials from height. 6. Continuous pouring of by same gang. 7. Revolving of oncrete mixer/vibrators. | 1. May affect Respiratory system. 2. Hands may get injured. 3. feet may get injured. 4. Can cause electrocution/asphyxiation. 5. Persons may get injured. 6. causes tiredness of workers and may lead to 7. Parts of body or clothes may get entrappd. | 3 | 3 | MODERATE | 3 | 1. Wear respirators or cover mouth and nose with wet cloth. 2. Use gloves and other PPE. 3. Use Safety Shoes. 4. Provide platform with wooden planking above reinforcement for movement of workers. 5. Ensure earthing of equipments and proper functioning of electrical circuit before commencement of work. 6. Use hard hats. 7. Remove surplus materil immediately from work place. 8. Ensure lighting arrangement during night hours. 9. Insist on shift pattern 10. Provide adequate rest to workers between subsequen 11. Allow only mixer with hooper. 12. Provide safety cages around moving motors. 13. Ensure proper mechanical locking of vibrator.
2 | Super - Structure | 1. Air pollution by cement. 2. Handling of Ingredients. 3. Protruding reinforced rods. 4. Earthing of electrical mixers, vibrartors etc.. Not done. 5. Falling of materials from height. 6. Continuous pouring of by same gang. 7. Revolving of oncrete mixer/vibrators. 8. Deflection in props or shuttering materials | 1. Shuttering / props may fall and collapseand prove fatal. | 4 | 3 | MODERATE | 3 | 1. Use PPEs like gloves,shoes, helmets, etc.. 2. Avoid usage of make -shift tools.
3 | Access to workplace | 1. Passage to workplace | 1. Improperly tied and designed props/planks may collapse | 3 | 3 | MODERATE | 3 | 1. Ensure the stability and strength of passage before commencement of work. 2. Do not overload or stand under the passage.
ACTIVITY - 5: OPERATION OF COMPACTOR..
1 | 1. Starting by pulling up with string. | 1. Inadvertent contact with vibrator. | 1. Accidents. 2. Damage. | 2 | 4 | MODERATE | 3 | 1. Pull the string gentally avoiding ontact or hit against compector or near by personal. 2. Guarding. 3. Hold firm and move slowly.
| 2. Running compactor. | 2. Rotating parts. 3. Fall.
ACTIVITY - 6: BRICK WORKS
1 | Storage of Bricks. | 1. Height above 1.5 2. Improper Storage | 1. Fall of Bricks 2. Personal Injury | 4 | 3 | MODERATE | 3 | 1.Restrict Height of Storage to 1.5 M. 2. Adopt cross bar system of storage.
2 | Transportation of bricks to the site. | 1. Unsecured bricks 2.Rough and uneven Road. | 1. Breakage of Bricks. 2. Personal Injury | 3 | 2 | LOW | 2 | 1. Ensure Bricks carried are properly secured. 2. Defensive Driving.
3 | Unloading Bricks. | 1. Fall of a bricks. 2.Wrong Lifting Method | 1. Personal Injury. 2. Back pain. | 4 | 3 | MODERATE | 3 | 1. Safe handling. 2. Education of correct posture.
4 | Shifting Bricks to the building site by Dumper. | 1. Use of defective dumper 2. Mis-Operation | 1. Damage to Dumper 2. Tilting of dumper | 3 | 4 | MODERATE | 3 | 1. Use servised dumper. 2. Deploy trained Operator. 3. Operate Slowly and carefully on rough road. 4. Provide trained Banksmen.
5 | Shifting Bricks, Cement mortar, concrete etc.,manually, (borrow). | 1. Defective Wheel barrow 2. Loosing balancedue to uneven/ loose surface 3. Absent mindedness. 4.Hurry. | 1. Overturning of wheelbarrow 2. Personnel Injury. | 3 | 2 | LOW | 2 | 1. Use good serviceable wheel barrow. 2. Use Planks wherever necessary. 3. Be cautious. 4. Concentrate on job. 5. Know your surroundings.
6 | Preparation of cement mortar and placing of bricks with cement. | 1. Improper handling of cement bags. 1. Evolution of cement dust at work place. 2. Splashing of cement | 1. Back pain. 2. Skin allergy. | 4 | 3 | MODERATE | 3 | 1. Fllow ergonomics. 2. Use of adequate PPE.
|  |  | 1. Dust allergy for workmen 2. Eye/skin injury. | 3 | 3 | LOW | 2 | 1. Use of adequate PPE.
ACTIVITY - 7: PLASTERING
1 | Plastering/Groutin g | 1. Inhalation of cement dust. 2. Absorption of cement. 3. Ingestion. | 1. Bronchial disease 2. Irritation. 3. Prolonged exposure causes dermatities. 4. Gastro-Instestinal | 4 | 3 | LOW | 2 | 1. Wear rspiratory protection. 2. Wear safety goggles and coverall. 3. Wash hands before taking food. 4. Take shower after reaching camp.
ACTIVITY - 8: SCAFFOLDING, FORMWORK AND LADDERS
1 | SCAFFOLEING, FORMWORK AND LADDERS | 1.Persons can fall down. 2. Failure of scaffolding material. 3. material can fall down. | 1. Person may sustain severe injuries and prove fatal. 2. Persons working at lower level get injured. | 4 | 3 | MODERATE | 3 | 1. provide guard rails for working at height. 2. Face ladder while climbing and use both hands. 3. Ladder shall extend about 1m above landing for easy access and tying up purpose. 4. Do notplace the ladder against amovable objects and maintain base at 1/4 ratio of the working length of the ladder. 5. Suspended scaffold shall not be less than 500mm wide and tied securely with ropes. 6. No loose planks shall be allowed.
7. Use PPE, like helmets, safety shoes etc.. 8. Inspect visually all scaffolding materials for stability and anchor with permanent structures. 9. Design scaffolding for max. load carrying capacity. 10. Scaffolding planks shall not be less than 250mm full thickness lumber or equivalent. These shall be cleated or 11. Do not overload the scaffolds. 12. Do not join short ladder to make alonge one. Vertical ladders shall not exceed 6m. 13. Remove excess material and scrap immediately. 14. Carry the tools only in a tool-kit bag. 15. Provide safety nets.
ACTIVITY - 9: CONCRETE MIXER OPERATION
| 1 | Deployment of Concrete pump | 1. Poor mechanical condition 2. Unauthorised operation | 1. Failure of equipment 2.Accident/Personal injury | 3 | 4 | MODERATE | 3 | 1. Use good serviced equipment. 2. Deploy only licenced operators. 3. Engage Banksman.
| 2 | Batching Plant. Truck Mixer. Cement bulk | 1. Poor mechanical condition 2. Unauthorised operation | 1. Failure of equipment 2. Accident/Personal injury | 4 | 3 | MODERATE | 3 | 1. Use good serviceable equipment. 2. Deploy only licenced operators. 3. Engage Banksman.
| 3 | Deployment of concrete mixture | 1. Improper placement of mixture machine on uneven 2. Mis-Operation 3. Loose contact with electric connection 4. Rotating parts of machine 5. Unblocked wheels of concete mixture 6. Improper coordination among crew members. 7. Smoke from the exhaust. | 1. Tilting of mixture. 2. Damage to concrete mixture. 3. Electrical shocks. 4. Fire hazard. 5. Personnel injury. 6.Unwanted movement of concretd of truk 7. Mis- operation and injury to rew. 8. Breathing Problems. | 4 | 3 | MODERATE | 3 | 1. Ensure concrete mixture is placed on even surface with proper pegs. 2. Check for proper electrical connetions and insullation. 3. Keep adequate fire extinguishers. 4. Proper guards at all rotating parts of mechinery. 5. Position the mixer machine to disperse smoke easly into atmoaphere. 6. Clean the mixer machine after the concreting is over.
ACTIVITY - 10: WORK ON REBAR
| 1 | Manual bar bending | 1. Defective tools. 2. wrong application of tools. 3. Wrong posture. | 1. Personal injury. 2. Damage to tools. 3. Back pain. | 2 | 3 | LOW | 2 | 1. Do not use sub-standard tools. 2. Ensure use of right tools for right job. 3. Do not push tools while bending. 4. Hold firmly 5. Adhere to connect and safe posture.
| 2 | Bar bending on bending machine | 1. Defective Machinery. 2. Difference in level between tble and machine. 3. Improper guard. 4. Inexperienced operator. | 1. Personal injury. 2. Damage to the machine. 3. Damage to the table. 4. Misoperation. | 3 | 3 | LOW | 2 | 1. Do not use defective tools. 2. Secure machine and table on level ground. 3. Keep area clean around machine. 4. Provide switch or emergency stoppage. 5. ensure guards are provided on all rotating parts. 6. hold the bars firmly. 7. Stack bars properly and away from machine.
| 3 | Manual cutting | 1. Toppling of chisel. 2. Slippage of bar under tension. | 1. Personal injury. 2. Flying bar. | 3 | 4 | MODERAT E | 3 | 1. Safe handling of tools. 2. Keep hand away from cutting chisel. 3. Hold bar firmly. 4. Ensure safet while operating handle.
| 4 | Binding bar with wire | 1. Haphazard placement of steel bar. | 1. Personal injury. | 3 | 3 | LOW | 2 | 1. Keep wires initially bend downward.
| 5 | Cutting bar by machine. | 1. Defective machine. 2. Improper guard. 3. Loose electrical connection. 4. Defective blade. | 1. Personal injury. 2. Damage to the machinery. 3. Personnel injury. 4. Fire hazard. 5. Personnel injury. | 4 | 3 | LOW | 2 | 1. Do not use deective tools. 2. Use serviced machine. 3.Provide stand on both sides of the machine for moving 4. Provide switch or emergency stoppage of machine. 5. Ensure proper electrical connections. 6. Do not use defective blades. 7. Keep hands away from cutting blade while in operation.
| 6 | Cutting wire by tools. | 1. Defective tools. | 1. Personal injury. 2. Damage to tools. | 3 | 3 | MODERAT E | 3 | 1. Use proper binding. 2. Take extra care while walking around the work site.
| 7 | Manual placement of bar. | 1. Loose binding of reinforcment. 2. Improper co-ordination. 3. Inexperienced persons. | 1. Slippage of binding steel reinforcement. 2. Personal injury. | 3 | 3 | LOW | 2 | 1. Ensure proper binding. 2. Give proper instructions. 3. Deploy trained and experienced persons. 4. Ensure proper co-ordination among the crew. 5. Avoid sharp edges.
ACTIVITY - 11: GRINDING
1 | Grinding and grinding wheel replacing | 1. Grinding without goggle. 2.Absence of tool rest on bench grinder. 3. More gap between the wheel and tool rest of bench 4. Improper/wrong size grinder wheel. 5. Excess pressure on wheel. 6. Breakage of wheel. | 1. Injury to eyes by flying 2. Accident and injury. | 3 | 4 | MODERAT E | 3 | 1. Use proper PPE. 2. Mount the tool rest on both side. 3. Replace the wheel. 4. Gap more than 3mm is unsafe. 5. Use grinding wheel of correct size. 6. Training and instruction. 7. Provide the extinguisher. 8. Use the blanket to cover nearby vents, drains, open ends of 9. Application of mud plug prior to pipe after cold cutting. 10. Proper tightening of wheel. 11. Use of corrct size spacer washers.
ACTIVITY - 12 HANDLING OF PORTABLE ELECTRICAL TOOLS
1 | Working with portable electrical tools. | 1. Damaged cable. 2. Defective tool. 3. loose components ( wheel, switch) 4. Excess pressure on tool. 5. Improper handling. 6. Non use of PPEs. | 1. Electric shock. 2. Spark/shock. 3.Hit injury. 4. Accident and injury. 5. Bodily injuy. 6. Shock/eye and bodily injuries. | 3 | 4 | MODERAT E | 3 | 1. Daily check up before start. 2. Replace defective tools. 3. Proper maintenance. 4. Training on proper use and care. 5. Inspection and corrective action to follow correct handling procedures. 6. Use aequatePPE ( Face shield/goggles, gloves).
ACTIVITY - 13: MATERIAL HANDLING (MANUAL)
1 | Material Handling (Manual) | 1. Non-use of PPEs. 2. Inadequate manpower. 3. Lack of co-ordination in group effort. 4. Wrong body posture. 5. Lifting error. 6. sharp edges/corners/projecting 7. Slippery materials. 8. Loos materials. | 1. Accident/injury. 2. Back pain, sprain, etc.. 3. property damage. 4. Injury/property damage. 5. Loss of property. | 3 | 4 | MODERAT E | 3 | 1. Use adequate PPE. 2. Provide adequate man power for lifting of heavy loads. 3. Training & instructions. 4. Use hand gloves/packing materials. 5. Remove protruding nails before handling. 6. use proper lifting devices for good grip. 7. Fasten the item properly or use suitable packing/ container.
ACTIVITY - 14: WORK AT HEIGHTS
1 | Working at elevated places. | 1. Person can fall down. 2. Material can fall down. | 1. May sustain severe injuries or prove fatal. 2. May hit scrap/material stacked at ground or in 3. May hit the workers working at lower levels and porove fatal. | 2 | 5 | HIGH | 4 | 1. Provide guardrails/barricade at the work place. 2. Use PPE like full body harnes, life line, helmets, safety shoes, etc.. 3. Obtain the permit before starting the work at height above 4. Fall arrest and safety nets, etc.. Must be installed. 5. Provide adequate working space ( min. 0.6m). 6. Tie/ weld working platform with fixed support. 7. Use roof top walk ladder while working on a slopping roofs. 8. Avoid movements on beam. 9. Keep the workplace neat and clean. 10. Remove the scrap immediately. 11. Do not throw or drop materials or equipment from height i.e. do not bomb materials. 12. All tools to be carried in a tool-kit bag or on working 13. Remove scrap from the planks. 14. Ensure wearing of helmet by the workers working at lower
ACTIVITY - 15: ERECTION, DISMENTALING AND WORKING ON SCAFFOLDING
1 | Scaffolding erection. | 1. Improper manual handling. 2. Fall of scaffolding materials. 3. Hitting. 4. Defective lifting equipment/Improper use. 5. Faulty erection. | 1. Personal injuries. 2. Material Damage. 3. Collapse of scaffolding and fall of persons. | 2 | 5 | HIGH | 4 | 1. Train on proper manual lifting procedures. 2. Use only tested and certified equipment & lifting tackles. 3. Erection only by experienced persons under supervision of a competent person. 4. Daily inspection and certification by competent person. 5. PTW in place.
2 | Working on scaffolding. | 1. Defective scaffolding. 2. Improperuse. 3. Faulty access to platform. 4. inadequate size of platform. 5. Overloading. 6. Faulty/unguarded access ladders/stairs. | 1. injury due to fall. | 1 | 5 | HIGH | 4 | 1. Daily inspection & certification by competent person. 2. Training & supervision. 3. Provide access/ladders or stairs_ as per specification. 4. adequate size as per job requirment. 5. No overloading permitted. 6. Only minimun number of persons allowed to work at time.
3 | Dismentalling scafolding | 1. fall of persons. 2. Fall of scaffolding materials. 3. fall of hand tools (hammer ). | 1. fatality / injury. | 1 | 5 | HIGH | 4 | 1. follow dismentaling procedures. 2. Do not allow persons to be under the scaffolding structure. 3. Use PPEs. 4. Keep tools in proper holder.
ACTIVITY - 16: SLIPS, TRIPS AND FALL AT WORK PLACE.
1 | Moving in the work area. | 1. Timbering blocks, wooden planks, steel rod bits. 2. Pipe pieces. 3. Protruding bolts on concrete foundations of pipe supports. 4. Paint tins,polythene papers, electric cable/wire insulations, steel wire insulations, steel | 1. Bodily injury due to fall of persons, fall of heavy objects,tools etc.. 2. Hitting on overhead projections. | 3 | 4 | MODERAT E | 3 | 1. Remove all timber blocks, planks, pipe pieces etc.. Immediately after use to the designated place. 2. Do not keep objects/tools etc. at height without safe containment against fall. 3. Provide barricading with warning tags. 4. Provide plastic/soft material cap to projectile pipes.
|  | 5. overhead projection of pipes. | [5 empty] | 5. Maintain good housekeeping by frquent appraisals, supervision, inspection, audit and follow up.
ACTIVITY - 17: WORKING IN DUSTY ENVIRONMENT
1 | Working in dust. | 1. Dust (inhalation and striking the eye) | 1. Lung disorders (silicosis) and eye injury. | 5 | 1 | MODERAT E | 3 | 1. Sprinkle water to supress dust generation wherever 2. Use PPE ( dust mask, goggles).
ACTIVITY - 18: FIRE PREVENTION AND PROTECTION.
1 | Fire prevention and protection. | 1. small fires can become big ones and may spread to the 2. Improper selection of fire extinguishers. 3. short circuiting of electrical system. | 1. Cause burn injuries and may prove fatal. 2. Complete extinguishment of fire may not be possible. 3. Can cause electrocution. | 3 | 4 | HIGH | 4 | 1. In case a fire breaks out, press fire alarm system and shout fire, fire. 2. Keep bucket full of sand and water/ fire extinguishers in all hazardous location. 3. Confine smoking to "smoking Zone" only. 4. Train people for using specific type of fire equipments under different classes of fire. 5. Maintain good housekeeping and first-aid boxes. 6. Do not obstruct access to fire extinguishers. 7. Do not use any sort of elevators for evacuation during fire. 8. Maintain lightening arrestors for elevated structures. 9. Stop all electrical motors. 10. move the vehicles from dangerous locations. 11. Remove the load hanging from the crane booms. 12. remain out of the danger areas. 13. Ensure usage of correct fire extinguisher meant for the specified fire. 14. Do not attempt to extinguish oil and electric fires with water. Use foam extinguishers/ CO2/sand. 15. Maintain safe distance of flammable substances from source of ignition. 16. restrict the distribution of flammable materials to only min. necessary amount. 17. Construct specifically designed fule storage facilities. 18. Kep chemicals in cool and dry place away from heat. Ensure adequate ventilation. 19. Before welding operation, remove or shild the flammable materials properly. 20. Store flammable materials in stable racks, correctly lebeled preferably with catchment trays. 21. Wipe off the spills immediately.