## 4 Plate Wheel
OM MAHABALI ENTERPRISES |  |  |  | CORRECTIVE ACTION PLAN IN 6W-2H FORMAT
Month - 05.01.2023
Legends : What – Defect Phenomenon Why - Cause Side-Indicate Root cause. Who – Responsible Person
Which – Shop / Cell / M/c /Stage How Much – Defective Qty. When - Target date for action completion.
Where – Process / Operation
How to Do – Indicate What is change in inspection side & Then what is cause side action taken & for sustenance updation in JH/PM/WI format.
Sr. No | What | Where | Which | Why | How much |  | How to do |  |  |  | INSPECTION SIDE |  |  | CAUSE SIDE |  |  | SUSTENANCE ACTION
[5 empty] | Actual | Target | INSPECTION SIDE |  | CAUSE SIDE
[7 empty] | BEFORE | AFTER | BEFORE | AFTER | Who | When | Status | Who | When | Status
1 | Operation Missing Part Found | At Endurance Assly Line | 4 Plate wheel | why(1) Operation Missing Part Found why(2) Due to Casting Materilas Stock Less at Lug Face | 1 Nos | 0 | 100 % Inspection Done as per Inspection Agreement | 1.100 % Inspection Done as per Inspection Agreement with Marking at Insert Face | Casting Materilas Stock Less at Lug Face | Casting Materilas stock 0.5 mm Increase at Lug Face | Inprocess Mr. Sagar & Santosh | 18.05.2022 | Completed | OME | 28.05.2023 | Completed | ……