## 6w1h
Bony Polymers (P) Ltd. |  |  |  |  | CORRECTIVE ACTION PLAN
Plot No-132 , Sector-24 Faridabad |  |  |  |  | Month: 22 Apr 2024
Legends : What – Other Damper Part Mixup Why - Similar Part matrix not displayed on inspection area Who – Inspection incharge
Which – Mixup Found Damper K4 in Damper 1402 How Much – 88 nos. out of 64720 nos. When - During incoming Inspection at Customer end
Where – Problem Found at Customer end
How to Do – By Gamba visit
Sr.No | WHAT | WHICH | WHERE |  | HOW MUCH |  | HOW TO DO |  |  |  | INSPECTION SIDE |  |  | CAUSE SIDE
[5 empty] | Actual | Target | Inspection Side |  | Cause Side |  | WHO | WHEN | STATUS | WHO | WHEN | STATUS
|  |  |  | Cause Side |  |  | Before | After | Before | After
1 | Other Damper Part Mixup | Other model part mixup in 1402 damper during the inspection at customer end. | at customer end | 1. Deflashing stage- During the deflashing 100 % part mixupwith Damper 1402 . 2. No identification in material storage bin. (Less awareness about the part). 3. Segregation & Inspection done at by same inspector. (Segregation & Inspection need to be in different place) | 20000 (One day deflashing production) | 0 | 1. Segregation & Inspection done at by same inspector. | 1. Different Table identified for Segregation and inspection. 2. For part identification similar part mixup sheet displayed at deflashing station. | 1.No identification tag in material storage bin | 1. identification tag provided in bin. 2. Awareness training about the identification tag and similar part provided to deflashing operator. | Mr. Nitesh | 26.04.2024 | OK | Mr. Nitesh | 26.04.2024 | OK

## working area
Deflashing Table
Inspection Table