## 6W2H
Part No / Name | When | What |  | Which | Where | How many | Why | Corrctive action |  | Who | When | Status
|  | Customer Complaint | Defect Phenomenon | Cell /Machine
Part No : JZ551400 Part Name : Gear Primary Helix | 20.06.2024 | Fitment issue | Burr fould at face | Gear Cell | Hobbing cell | 35 | Detection Side: W1: Burr fould at face. W2: Operator not aware face burr fould. Cause Side W1: Burr fould at face. W2: During hobbing burr not proper removed. W3: Deburring disc not proper set during hobbing. Root Cause: Deburring disc not proper set during hobbing. | Detection Side Action: 1) At Final inspection stage 100% face burr inspection started and identification by paint marker. 2) OJT given to all concern inspector regarding no burr fould at face. Cause Side action: 1. Proper deburring disc set. 2. Training given to all concern setter regarding deburring disc settingl |  | Mr.Bade Mr.Bade Mr.Tak Mr.Tak | 20.06.2024 20.06.2024 20.06.2024 20.06.2024 | C C C C
;
Preventive action |  | Target date | Status | Sustenance action | Tgt date | Status | System action | Tgt date | Status
During setting first 5 components ensure no burr fould. |  | 20.06.2024 | On going activity | Verification during setting approval | 20.06.2024 | On going activity | Point added in setting approval report | 20.06.2024 | C